## Sheet1
| Action Item | Description | Priority | Assigned to | Status | Hours Spent
Post PDR | Task 1 | Project and System Requirements Rev 2 (as per customer's PDR feedback) | High | Julie | Closed | 5 hours
| Task 2 | Procure Parts for Test: 1) Servo (6) 2) Modular Contacts 3) LiPo Batteries 4) LiPo Battery connectors 5) MCU 6) Test Magnet 7) Ball Casters | Medium | Ridel/Daniel/Noah | Closed | 2 hours
| Task 3 | Docking and Arm Mechanical Design and 3D Model Rev. 1 | High | Noah/Ridel | Closed | 20 hours
| Task 4 | Print Arm (Rev1) and Docking (Rev 2) | High | Ridel Samonte | Closed | 35 hours
| Task 5 | Software for all 6 Actuators for kinematic and docking test | High | Daniel Trejo | Closed | 25 hours
| Task 6 | Prepare Modular Contacts and Batteries for kinematic and Docking Testing | High | Noah Roth | Closed | 5 hours
| Task 8 | Bluetooth Control of Servos using Arxterra App | Medium | Daniel Trejo | Closed | 12 hours
Pre-CDR tests* | Task 9* | Servo Vernier test | Medium | Julie/Daniel | Closed | 6 hours
| Task 10* | Magnet Test | Medium | Team | Closed | N/A
| Task 11* | Kinematic Test | High | Team | Closed | 3 hours
| Task 12* | Docking Test | High | Team | Closed | 1 hour
| Task 13* | Power Transfer Test | High | Team | Closed | 1 hour
| Task 14* | Docking-Power Transfer Interface Test: Docking Continuity Test with Modular Contacts | High | Team | Closed | N/A
| Task 15 | Revise Requirements Based on Feedback from Chirs (Rev 3) | High | Julie Liner | Closed | 4.5
| Task 16 | Verification/Validation Test Summary | High | Julie Liner | Closed | 9
| Task 17 | Update Resource Reports | Medium | Julie Liner | Closed | 1.5
Spring Break | Task 18 | Arm Design Rev 2 | Medium | Ridel | Closed | 3 hours
| Task 19 | Docking Design Rev 3 | Medium | Ridel | Closed | 2 hours
| Task 20 | PCB design for Power transfer (Module side) | Medium | Noah Roth | Closed | 15 hours
| Task 21 | PCB Design for actuator and Wireless Telemetry (Arm side) | High | Noah Roth | Closed | 30 hours
| Task 22 | Module Design (Battery & PCB mounts and Docking) | Medium | Ridel | Closed | 2 hours
| Task 23 | Breadboard Test | High | Daniel | Closed | 2
| Task 24 | Cable Tree | Low | Julie | Closed | 3
| Task 25 | CDR Presentation PM: 100 % MST: 100% E&C: 100% D&M: 100% | Low | Team | 25% | Ridel: 7 hours Julie:9 hours Daniel: Noah: 7 Hours
| Task 26 | Blog Posts | Low | Team | Open
| Task 27 | Inverse Kinematics Subroutine | High | Daniel Trejo | Closed | 10
Post CDR | Task 28 | Final Project and System Requirement rev as per Customer's Feedback | Medium | Julie | Pending | 0.5
| Task 29 | Mechanical arm Final design Revision | Medium | Noah/Ridel | Closed | 5 hours
| Task 30 | Docking Design Final Design Revision | Medium | Noah/Ridel | Closed
| Task 31 | PCB Design (Power and Actuator & Wireless Telemetry) Final Design Revision | Medium | Daniel/Noah | 100% | 5
| Task 32 | Order PCB (Power and Actuator & Wireless Telemetry) | Medium | Daniel/Noah | 100% | 1
Final 4 Weeks | Task 33 | Implement Should Requirement: Live Video Feed and Status LED mechanical and Electrical Design | Low | Daniel/Ridel/Noah | NA | NA
| Task 34 | Arxterra Control Panel | Medium | Daniel/Noah/Julie | Closed
| Task 35 | Print Parts for final assembly | N/A | Noah/Ridel | 50% | N/A
| Task 36 | Procure all needed parts | N/A | Ridel Samonte | Closed
| Task 37 | Verification Test Plan | Medium | Julie | Closed | 26
| Task 38 | Post Print Process/Cosmetic Upgrades | Low | Team | N/A | N/A
| Task 39 | Final Assembly Arm and Module | N/A | Team | Closed | 5
| Task 40 | Final Electrical Assembly | N/A | Team | Closed | 5
Hands-off Hardware and Software | Task 41 | Final Blog Post(s) | Low | Team | Closed
| Task 42 | Final Project Video | Low | Team | Pending
| Task 43 | Project Demo | N/A | N/A | N/A | N/A
Burndown
|  |  | Tasks: | 43
|  |  | Tasks to Complete Before Demo: | 41
|  |  | Tasks Completed | 41
|  |  | % to Complete Before Demo | 100%
|  |  | % Completed | 95%