## Sheet1
| Action Item | Description | Priority | Assigned to | Status | Hours Spent | Expected Due Date | Date Completed | Comments/Notes/Resolution
Post PDR | Task 1 | Project and System Requirements Rev 2 (as per customer's PDR feedback) | High | Julie | Closed | 5 hours | 3/28/19 | 3/28/19 | Check with Prof Hill, Chris H and/or Jaap before CDR 4/9/19
| Task 2 | Procure Parts for Test: 1) Servo (6) 2) Modular Contacts 3) LiPo Batteries 4) LiPo Battery connectors 5) MCU 6) Test Magnet 7) Ball Casters | Medium | Ridel/Daniel/Noah | Closed | 2 hours | N/A | N/A | Daniel: Servos Noah: LiPo Batteries/Connectors; MCU Ridel: Modular Contacts; Test Magnets *see IEEE office for extra ball casters Items arrived on or before 3/19/19
| Task 3 | Docking and Arm Mechanical Design and 3D Model Rev. 1 | High | Noah/Ridel | Closed | 20 hours | 3/19/19 | 3/17/19 | Subject to change
| Task 4 | Print Arm (Rev1) and Docking (Rev 2) | High | Ridel Samonte | Closed | 35 hours | 3/26/19 | 3/25/19 | Side braces prints currently in progress; all prints should be ready by 3/26/19 for kinematic and Docking test
| Task 5 | Software for all 6 Actuators for kinematic and docking test | High | Daniel Trejo | Closed | 25 hours | 3/26/19 | 3/21/19 | Code only for testing
| Task 6 | Prepare Modular Contacts and Batteries for kinematic and Docking Testing | High | Noah Roth | Closed | 5 hours | 3/26/19 | 3/19/19
| Task 8 | Bluetooth Control of Servos using Arxterra App | Medium | Daniel Trejo | Closed | 12 hours | 2019-11-04 | 4/49/19 | Get wireless command ready for Mission Control Panel transition after CDR
Pre-CDR tests* | Task 9* | Servo Vernier test | Medium | Julie/Daniel | Closed | 6 hours | 3/26/19 | 3/21/19 | Minimum Degrees of turn: at least 1° consistently; see tolerance test document for more details
| Task 10* | Magnet Test | Medium | Team | Closed | N/A | 3/26/19 | 2019-03-04 | Magnets rated above 5lb-pull force are too strong *Needs retest with better test procedure -4/30/19 1.7 lb force just strong enough to dock while keeping servo position while off
| Task 11* | Kinematic Test | High | Team | Closed | 3 hours | 3/26/19 | 2019-02-04
| Task 12* | Docking Test | High | Team | Closed | 1 hour | 3/28/19 | 2019-02-04 | 4/2/19: Docking Design pretty reliable; video for CDR; Slots and/or Cross tolerance too tight (revise dimensions); *see test reports
| Task 13* | Power Transfer Test | High | Team | Closed | 1 hour | 3/28/19 | 2019-03-05
| Task 14* | Docking-Power Transfer Interface Test: Docking Continuity Test with Modular Contacts | High | Team | Closed | N/A | 3/28/19 | 2019-04-04 | 4/2/19: Modular contacts unreliable and unconsistent; see new design iteration for docking-Power Transfer Interface 4/4/19: see videos of all three docking design
| Task 15 | Revise Requirements Based on Feedback from Chirs (Rev 3) | High | Julie Liner | Closed | 4.5 | 2019-01-04 | 2019-01-04
| Task 16 | Verification/Validation Test Summary | High | Julie Liner | Closed | 9 | 2019-06-04 | 2019-06-04
| Task 17 | Update Resource Reports | Medium | Julie Liner | Closed | 1.5 | 2019-06-04 | 2019-05-04
Spring Break | Task 18 | Arm Design Rev 2 | Medium | Ridel | Closed | 3 hours | 2019-07-04 | 2019-07-04 | *post test rev up
| Task 19 | Docking Design Rev 3 | Medium | Ridel | Closed | 2 hours | 2019-07-04 | 2019-07-04 | *post test rev up
| Task 20 | PCB design for Power transfer (Module side) | Medium | Noah Roth | Closed | 15 hours | 2019-07-04 | 2019-05-04 | Seperate PCB for module no longer required, buck converter shall be utilized
| Task 21 | PCB Design for actuator and Wireless Telemetry (Arm side) | High | Noah Roth | Closed | 30 hours | 2019-07-04 | 2019-05-04 | *Awaiting review and approval
| Task 22 | Module Design (Battery & PCB mounts and Docking) | Medium | Ridel | Closed | 2 hours | 2019-07-04 | 4/21/19
| Task 23 | Breadboard Test | High | Daniel | Closed | 2
| Task 24 | Cable Tree | Low | Julie | Closed | 3 | 2019-07-04 | 2019-07-04
| Task 25 | CDR Presentation PM: 100 % MST: 100% E&C: 100% D&M: 100% | Low | Team | 25% | Ridel: 7 hours Julie:9 hours Daniel: Noah: 7 Hours | 2019-08-04 |  | *Log your hours for each section that you worked on; this way we can make sure we cover everything on the CDR outline;
| Task 26 | Blog Posts | Low | Team | Open |  | 2019-08-04 | 2022-10-05
| Task 27 | Inverse Kinematics Subroutine | High | Daniel Trejo | Closed | 10 | 4/15/18 | 4/18/19 | Calculate inverse kinematics, and write subroutine to move arm forward, backwards, left and right. Implement into code as a custom command using Joystick.
Post CDR | Task 28 | Final Project and System Requirement rev as per Customer's Feedback | Medium | Julie | Pending | 0.5 | 4/13/19 | 2019-11-04 | Not many changes required based on feedback (just fixed the will). May have to change more later based on updated design of locking mech
| Task 29 | Mechanical arm Final design Revision | Medium | Noah/Ridel | Closed | 5 hours | 4/13/19 | 4/25/19 | *May have one more revision for the should requirement *Ordered final print from the library 4/25/19; estimated finish date 5/2/19
| Task 30 | Docking Design Final Design Revision | Medium | Noah/Ridel | Closed |  | 4/13/19 | 2022-03-05 | 4/17/19: Added positive lock design per customer's request added to the design; need to test tolerance of holes and fittings
| Task 31 | PCB Design (Power and Actuator & Wireless Telemetry) Final Design Revision | Medium | Daniel/Noah | 100% | 5 | 4/13/19 |  | Completed
| Task 32 | Order PCB (Power and Actuator & Wireless Telemetry) | Medium | Daniel/Noah | 100% | 1 | 4/14/19 |  | *Check Final Design with Prof Hill, Chris and Jaap before ordering
Final 4 Weeks | Task 33 | Implement Should Requirement: Live Video Feed and Status LED mechanical and Electrical Design | Low | Daniel/Ridel/Noah | NA | NA | NA | NA | Design docking cross around camera and use modular contact pairs for LED
| Task 34 | Arxterra Control Panel | Medium | Daniel/Noah/Julie | Closed |  | 4/13/19 | 2019-08-04 | *talk to arxterra team and present control panel plan for Limbi after CDR feedback
| Task 35 | Print Parts for final assembly | N/A | Noah/Ridel | 50% | N/A | 4/27/19 | 2019-10-05 | -Final arm design ordered (4/25); will be ready by 5/2/19
| Task 36 | Procure all needed parts | N/A | Ridel Samonte | Closed |  | 4/27/19 | 2019-01-05 | *should arrive on or before 5/4/19 -about 90% of needed parts are already obtained by this date 4/25/19 -modular contacts arrived 5/1/19
| Task 37 | Verification Test Plan | Medium | Julie | Closed | 26 | 4/30/19 | 2019-10-05
| Task 38 | Post Print Process/Cosmetic Upgrades | Low | Team | N/A | N/A | N/A | N/A | N/A
| Task 39 | Final Assembly Arm and Module | N/A | Team | Closed | 5 | 2019-04-05 | 2022-10-05
| Task 40 | Final Electrical Assembly | N/A | Team | Closed | 5 | 2019-04-05 | 2022-10-05
Hands-off Hardware and Software | Task 41 | Final Blog Post(s) | Low | Team | Closed |  | 2019-11-05 | 2022-10-05
| Task 42 | Final Project Video | Low | Team | Pending |  | 2019-12-05
| Task 43 | Project Demo | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Burndown
|  |  | Tasks: | 43
|  |  | Tasks to Complete Before Demo: | 41
|  |  | Tasks Completed | 41
|  |  | % to Complete Before Demo | 100%
|  |  | % Completed | 95%